## Gantt Chart Template
Task Name | Start (Date) | End (Date) | Duration (Days)
T1 Tank Design | 2023-10-24 | 2023-10-31 | 7
T1 Microcontroller and Sensor Configuration | 2023-11-01 | 2023-11-14 | 13
T2 Setting up Cloud | 2023-11-15 | 2023-11-21 | 6
T2 Database Creation | 2023-11-22 | 2023-12-05 | 13
T3 Data Visualization (User Interface) | 2023-12-06 | 2023-12-26 | 20
T4 Testing and Troubleshooting | 2023-12-27 | 2024-01-09 | 13
T4 User Manual | 2024-01-10 | 2024-01-16 | 6
T5 Final Testing and Deployment | 2024-01-17 | 2024-01-23 | 6
45223
45224
Free Related Templates
Project Plan Template for Word
Project Budget Template for Excel
Project Dashboard Template for Excel
FISH FARM MANAGEMENT SYSTEM
Project Timeline (Group no 20)

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!